# Formal Phased Project Breakdown
Phase/Activity	Duration (days)	Due date/ Milestone
1.Research and Design
1.1 Decide upon project and create summary	3	Sept. 16 - Milestone 1 - Deliverable 1
1.2 Create Preliminary Design document	12	Oct. 7 - Milestone 2 - Deliverable 2
1.3 Research and decide upon music playing library	1	Oct 21 - Milestone 3
1.4 Determine what files are acceptable or if conversion will be possible (if so... research libraries)	1	Oct 21 - Milestone 3
1.5 Decide what kind of statistics and reporting will be done and research graphing/plotting libraries	1	Oct 21 - Milestone 3
1.6 Figure out what preferences and settings will be configurable and where they will be stored	1	Oct 21 - Milestone 3
1.7 Research and decide upon streaming APIs	1	Oct 21 - Milestone 3
1.8 Research and decide upon method of implementing distributed system	1	Oct 21 - Milestone 3
1.9 Determine traits of songs which playlist generator can base selection on; decide on algorithms to use (hill climbing)	1	Nov 4 - Milestone 3
1.10 Decide on classes and responsibilities for playlists	1	Nov 4 - Milestone 3
1.11 Decide upon how to implement database	1	Nov 4 -Milestone 3
1.12 Create UI designs	5	Nov 4 - Milestone 4
1.13 Requirements Document	6	Nov 4 - Milestone 4 - Deliverable 3
1.14 Design Document	12	Jan 27 – Milestone 8 - Deliverable 4
1.15 Implementation Document	12	Feb 17 – Deliverable 5 – Milestone 10
2. Music Player
2.1 Experiment with library and create simple music playing program	2	Nov 18 - Milestone 5
2.2 Implement a music queue to hold a configurable number of songs to play in sequence	2	Nov 18 - Milestone 5
2.3 Extend music playing program to have all desired actions (skip, play, pause, stop, repeat, etc.)	3	Nov 18 - Milestone 5
2.4 Extend music playing program to accept streaming songs; perhaps detect quality of streaming songs to switch to local files if quality is low	4	Dec 2 - Milestone 6
2.5 Create and run unit tests	2	Dec 2 - Milestone 6
2.6 Integrate music player	1	Dec 2 - Milestone 6
3. Streaming Manager
3.1 Implement manager to accept requests from request manager and direct to player	4	Nov 18 - Milestone 5
3.2 Unit tests	1	Dec 2 - Milestone 6
3.3 Integrate	1	Dec 2 - Milestone 6
4. Playlist Manager
4.1 Implement playlist, playlist manager, and song classes according to design	1	Nov 18 – Milestone 5
4.2 Unit test	0.5	Nov 18 – Milestone 5
4.3 Integrate	0.5	Dec 2 – Milestone 6
5. Request Handler
5.1 Set up simple server that detects requests and returns simple response	3	Nov 18 - Milestone 5
5.2 Generate more complex interface for server to allow song requests, feedback submission, and song list request	2	Nov 18 - Milestone 5
5.3 Implement streaming music requests	4	Dec 2 - Milestone 6
5.4 Unit tests	1	Dec 2 - Milestone 6
5.5 Integrate	1	Dec 2 - Milestone 6
6. Database Interface
6.1 Create program to set up database	1	Jan 11 - Milestone 7
6.2 Create interface and querying classes for database	1	Jan 11 - Milestone 7
6.3 Unit tests	1	Jan 11 - Milestone 7
6.4 Integrate	2	Feb 17 - Milestone 9
7. Intelligent Playlist Generator
7.1 Implement simple generator based on hard coded preference	2	Jan 11 - Milestone 7
7.2 Make weights or evaluation functions configurable	1	Jan 11 - Milestone 7
7.3 Unit tests	1	Jan 11 - Milestone 7
7.4 Create playlist generator UI for configuration	3	Feb 17 - Milestone 9
7.5 Integrate	2	Feb 17 - Milestone 9
8. Statistics and Reports
8.1 Implement according to design	2	Jan 11 - Milestone 7
8.2 Create unit tests	1	Jan 11 - Milestone 7
8.3 Integrate to get data from other modules	1	Jan 11 - Milestone 7
8.4 Create image/report viewing UI/Viewer	3	Feb 17 - Milestone 9
8.5 Integrate UI	2	Feb 17 - Milestone 9
9. Phone Application
9.1 Create simple program to send requests to request module and process feedback	2	Mar 5 - Milestone 10
9.2 Extend to display song list; allow selection of song and sending of request; extend to send user feedback	2	Mar 5 - Milestone 10
9.3 Implement remaining features along with desired UI (assuming it was designed)	5	Mar 19 - Milestone 11
9.4 Unit tests	2	Mar 19 - Milestone 11
10. User Interface
10.1 Create main menu interface	4	Mar 5 - Milestone 10
10.2 Unit test	1	Mar 5 - Milestone 10
11. Integrate & Test
11.1 Integrate all components into main menu	4	Mar 19 - Milestone 11
11.2 Improve overall integration	21	Apr 26 - Milestone 13
11.3 Test fully integrated software	21	Apr 26 - Milestone 13

# Milestones
	Title	Result	Date	Dependencies	Deliverables
1	Group Formation	Group formed and project determined	09/16/11	M1	1. Project summary
2	Preliminary Design	Create Preliminary Design Document	10/07/11	M1	2. Preliminary Design
3	Research	Research necessary libraries and software for modules; decide upon most requirements for implementation	10/21/11	M1
4	Requirements Document	Create Requirements Document	11/04/11	M1, M3	3. Requirements Document
5	Primary Modules I	Start music player, streaming manager, playlist manager and request handling modules	11/18/11	M1, M3
6	Primary Modules II	Finish music player, streaming manager, and request handling modules	12/02/11	M1, M3, M5
7	Secondary Modules I	Start statistics, preferences, and AI modules	01/11/12	M1, M3
8	Design document	Create design document	01/27/12	M1, M3, M4	4. Design Document
9	Secondary Modules II	Finish statistics, preferences, and AI modules; implementation document	02/17/12	M1, M3, M5, M6, M7	5. Implementation Document
10	Phones and UI	Start phone applications and create main UI	03/05/12	M1, M3	6. Milestone Demo
11	Phones and Integrate	Finish phone applications and complete integration	03/19/12	M1, M3, M5, M6, M7, M9, M10
12	Presentation	Class presentation	04/09/12	M1, M3, M5, M6, M7, M9, M10, M11	7. Class Presentation
13	Integrate and Test	Integrate and test; hand in final project	04/26/12	M1, M3, M5, M6, M7, M9, M10, M11	8. Application Acceptance Test

# Meetings
Meetings with the client, Joseph Vybihal, will ideally take place within a few days of each milestone.